## Gantt Chart
Gantt Chart
TITLE: Rice Type Classification & Extent Prediction | [6 empty] | COMPANY NAME: |  |  |  |  | Danny The Analyst
PROJECT MANAGER: Daniel Ihenacho | [6 empty] | CREATION DATE: |  |  |  |  | 2024-03-03
MILESTONES & TASK ID NUMBER | TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [8 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
MARCH
[7 empty] | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
EDA REPORT | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1.1 | Download Dataset | Rice Industry Experts | 2024-03-03 | 2024-03-04 | 1 | 0% | bar: MARCH S 3 to MARCH M 4
1.2 | Create Project Workspace | Data Scientists | 2024-03-04 | 2024-03-05 | 1 | 0% | bar: MARCH M 4 to MARCH T 5
1.3 | Clean Data | Data Scientists/Analysts | 2024-03-05 | 2024-03-06 | 1 | 0% | bar: MARCH T 5 to MARCH W 6
1.4 | Perform Exploratory Data Analysis | Data Analysts | 2024-03-06 | 2024-03-09 | 3 | 0%
1.1 | Download Dataset | Rice Industry Experts | 2024-03-03 | 2024-03-04 | 1 | 100%
1.2 | Create Project Workspace | Data Scientists | 2024-03-04 | 2024-03-05 | 1 | 100%
1.3 | Clean Data | Data Scientists/Analysts | 2024-03-05 | 2024-03-06 | 1 | 100%
1.4 | Perform Exploratory Data Analysis | Data Analysts | 2024-03-06 | 2024-03-09 | 3 | 100%
FEATURE ENGINEERING
2.1 | Outlier Treatment | Data Scientists | 4/12 | 4/14 | 3 | 0% | bar: MARCH S 31
2.2 | Data Normalisation | Data Scientists | 4/15 | 4/16 | 2 | 0%
2.3 | Clustering Analysis | Data Scientists & Analysts | 4/19 | 4/30 | 10 | 0%
2.1 | Outlier Treatment | Data Scientists | 2024-03-10 | 2024-03-11 | 1 | 100%
2.2 | Data Normalisation | Data Scientists | 2024-03-11 | 2024-03-12 | 1 | 100%
2.3 | Clustering Analysis | Data Scientists & Analysts | 2024-03-12 | 2024-03-15 | 3 | 100%
MODEL TRAINING & EVALUATION
3.1 | Develop Machine learning and Deep Learning Classification Algorithms | Data Scientists | 2024-03-17 | 2024-03-18 | 1 | 100%
3.2 | Develop Machine learning and Deep Learning Regression Algorithms | Data Scientists | 2024-03-18 | 2024-03-19 | 1 | 100%
3.3 | Evaluate Classification and Regression Algorithms | Data Scientists | 2024-03-19 | 2024-03-20 | 1 | 100%
DOCUMENTATION & REPORTING
4.1 | Create README.md file | Data Scientists | 2024-03-21 | 2024-03-22 | 1 | 100%
4.2 | Reorganise Project Workspace | Data Scientists & Analysts | 2024-03-21 | 2024-03-22 | 1 | 100%
4.3 | Develop Necessary Project Files | Project Manager | 2024-03-21 | 2024-03-23 | 2 | 100%
PUSH PROJECT TO GITHUB REPOSITORY
5.1 | Create GitHub Repository | Data Scientists | 2024-03-21 | 2024-03-22 | 1 | 100%
5.2 | Push Project to GitHub Repository | Data Scientists | 2024-03-21 | 2024-03-22 | 1 | 100%
5.3 | Share Project as a LinkedIn Post | Project Sponsor | 2024-03-22 | 2024-03-24 | 2 | 100%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])