## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
EDA REPORT | 1.1 | Download Dataset | Rice Industry Experts | 1
| 1.2 | Create Project Workspace | Data Scientists | 1
| 1.3 | Clean Data | Data Scientists/Analysts | 1
| 1.4 | Perform Exploratory Data Analysis | Data Analysts | 3
FEATURE ENGINEERING | 2.1 | Outlier Treatment | Data Scientists | 1
| 2.2 | Data Normalisation | Data Scientists | 1
| 2.3 | Clustering Analysis | Data Scientists & Analysts | 3
MODEL TRAINING & EVALUATION | 3.1 | Develop Machine learning and Deep Learning Classification Algorithms | Data Scientists | 1
| 3.2 | Develop Machine learning and Deep Learning Regression Algorithms | Data Scientists | 1
| 3.3 | Evaluate Classification and Regression Algorithms | Data Scientists | 1
DOCUMENTATION & REPORTING | 4.1 | Create README.md file | Data Scientists | 1
| 4.2 | Reorganise Project Workspace | Data Scientists & Analysts | 1
| 4.3 | Develop Necessary Project Files | Project Manager | 2
PUSH PROJECT TO GITHUB REPOSITORY | 5.1 | Create GitHub Repository | Data Scientists | 1
| 5.2 | Push Project to GitHub Repository | Data Scientists | 1
| 5.3 | Share Project as a LinkedIn Post | Project Sponsor | 2